## Slide 1
DEPARTMENT OF CSE
COURSE NAME – ADAPTIVE Software Engineering
COURSE CODE – 22CS2119R
Topic:
PROJECT PLANNING ESTIMATION

## Slide 2
AIM OF THE SESSION
To familiarize students with the basic concept of Project planning and estimation
INSTRUCTIONAL OBJECTIVES
This Session is designed to:
This Session is designed to:
1.Describe Project estimation
2Explain Function Point Analysis 3.Describe COCOMO Software Estimation Model
LEARNING OUTCOMES
At the end of this session, you should be able to:
1 Define project estimation
2. Demonstrate the order in which the following are estimated using the COCOMO estimate technique, use a schematic diagram and a relevant example: Cost, effort, length of time, and size .

## Slide 3
Project estimation
Lines of code
Function point analysis
COCOMO MODEL
AGENDA

## Slide 4: Project estimation
Estimation determines how much money, effort, resources, and time will be required to build a specific system or product. Project estimation may involve the following:
Software size estimation
Effort estimation
Time estimation
Cost estimation
Software size estimation
It helps the project manager to predict the effort and time which will be needed to build the project. The following measures are used for size estimation:
Lines of Code
Number of entities in ER diagram
Total number of processes in detailed data flow diagram
Function points

## Slide 5
Lines of Code
LOC count the total number of lines of source code in a project. The units of LOC are:
KLOC- Thousand lines of code
NLOC- Non comment lines of code
KDSI- Thousands of delivered source instruction
Advantages
Universally accepted and is used in many models like COCOMO.
Estimation is closer to developer’s perspective.
Simple to use.
Disadvantages
Different programming languages contains different number of lines.
No proper industry standard exist for this technique.
It is difficult to estimate the size using this technique in early stages of project.

## Slide 6: Total number of processes in detailed data flow diagram
Data Flow Diagram(DFD) represents the functional view of a software. The model depicts the main processes/functions involved in software and flow of data between them. Utilization of number of functions in DFD to predict software size. Already existing processes of similar type are studied and used to estimate the size of the process. Sum of the estimated size of each process gives the final estimated size.
Advantages
It is independent of programming language.
Each major processes can be decomposed into smaller processes. This will increase the accuracy of estimation
Disadvantages
Studying similar kind of processes to estimate size takes additional time and effort.
All software projects are not required to construction the DFD.

## Slide 7: Function Point Analysis
In this method, the number and type of functions supported by the software are utilized to find FPC (function point count). The steps in function point analysis are:
Count the number of functions of each proposed type
Compute the Unadjusted Function Points (UFP)
Find Total Degree of Influence (TDI)
Compute Value Adjustment Factor (VAF)
Find the Function Point Count (FPC)

## Slide 8
Function Point Analysis: Continue
(1) Count the number of functions of each proposed type
Find the number of functions belonging to the following types:
External Inputs: Functions related to data entering the system.
External outputs: Functions related to data exiting the system.
External Inquiries: They leads to data retrieval from system but don’t change the system.
Internal Files: Logical files maintained within the system. Log files are not included here.
External interface Files: These are logical files for other applications which are used by our system.

## Slide 9
(2) Compute the Unadjusted Function Points (UFP):
Categorize each of the five function types as simple, average or complex based on their complexity. Multiply count of each function type with its weighting factor and find the weighted sum.
Weighting factors for each type
based on their complexity
Function type | Simple | Average | Complex
External Inputs: | 3 | 4 | 6
External outputs | 4 | 5 | 7
External Inquiries | 3 | 4 | 6
Internal Files | 7 | 10 | 15
External interface Files | 5 | 7 | 10

## Slide 10: (3) Find Total Degree of Influence (TDI)
Use the ’14 general characteristics’ of a system to find the degree of influence of each of them. The sum of all 14 degrees of influences will give the TDI. The range of TDI is 0 to 70. The 14 general characteristics are: Data Communications, Distributed Data Processing, Performance, Heavily Used Configuration, Transaction Rate, On-Line Data Entry, End-user Efficiency, Online Update, Complex Processing Reusability, Installation Ease, Operational Ease, Multiple Sites and Facilitate Change. Each of above characteristics is evaluated on a scale of 0-5.
(4) Compute Value Adjustment Factor (VAF):
Use the following formula to calculate VAF.
VAF = (TDI * 0.01) + 0.65
(5) Find the Function Point Count:
Use the following formula to calculate FPC.
FPC = UFP * VAF

## Slide 11
Advantages
It can be easily used in the early stages of project planning.
It is independent on the programming language.
It can be used to compare different projects even if they use different technologies(database, language etc).
Disadvantages
It is not good for real time systems and embedded systems.
Many cost estimation models like COCOMO uses LOC and hence FPC must be converted to LOC.

## Slide 12: COCOMO Model (Constructive cost model)
Introduction
It is one of the most widely used for software estimation model in the world
It was developed by Berry Boehm in 1981.
COCOMO model predicts the efforts and schedule for a software development based on the input related to size of the software and a numbers of the cost drivers that effects the productivity.
COCOMO Models
Based on the complexity of the project, COCOMO has three following models:
Basic COCOMO model
Intermediate COCOMO model
Detailed COCOMO model

## Slide 13: The Development Modes: Project Characteristics
Organic Mode
Relatively small, simple software projects
Small teams with good application experience work to a set of less than rigid requirements
Similar to the previously developed projects relatively small and requires little innovation
Semi-detached Mode
Intermediate (in size and complexity) software projects in which teams with mixed experience levels must meet a mix of rigid and less than rigid requirements.

## Slide 14: Embedded Mode Software Projects That Must Be Developed Within A Set Of Tight Hardware, Software, And Operational Constraints.
Embedded Mo

## Slide 15
Assumptions:
Primary cost driver is the number of Delivered Source Instructions (DSI) / Delivered Line Of Code developed by the project.
COCOMO estimation assume that the project will enjoy good management by both the developer and the customer.
Assume the requirements specification is not substantially changed after the plans and requirements phase.

## Slide 16: Basic COCOMO
Basic COCOMO is good for quick, early, rough model to estimate the software efforts and costs.
It does not account for differences in hardware constraints, personnel quality and experience, use of modern tools and techniques, and other project attributes known to have a significant influence on software costs, which limits its accuracy.

## Slide 17: Basic COCOMO Model: Formula
1. EPM
DMonths
P
E: The effort applied in person-months.
D: The development time in chronological months.
KLOC/KDSI: the estimated number of delivered lines of code for the project (expressed in thousands).
P: The number of people required.
Note: The effort and the duration estimations obtained using the COCOMO model are called as nominal effort estimate and nominal duration estimate.

## Slide 18
Coefficient a, b, c, and d:
Software project | a | b | c | d
Organic | 2.4 | 1.05 | 2.5 | 0.38
Semi- detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 3.6 | 1.20 | 2.5 | 0.32

## Slide 21
Problem-1: Assume that the size of an organic type software product has been estimated to be 32,000 lines of source code. Assume that the average salary of software engineers be Rs. 15,000/- per month. Determine the effort required to develop the software product and the nominal development time.
Solution: As per the basic COCOMO estimation formula for organic software: Effort=2.4*(32)1.05
= 91 PM
Nominal development time = 2.5 * (91)0.38 = 14 months Cost required to develop the product = 14 * 15,000 = Rs. 210,000/-

## Slide 22: Problem 2: Suppose That A Project Was Estimated To Be 400 KLOC. Calculate The Effort And Development Time For Each Of The Three Modes I.E. Organic, Semidetached And Embedded.
Solution: Estimated size of the project = 400 KLOC
1. Organic Mode
E = 2.4 (400)1.05 = 1295.31 PM
D = 2.5 (1295.31)0.38 = 38.07 M
2. Semi detached Mode
E = 3.0 (400)1.12 = 2462.79 PM
D = 2.5 (2462.79)0.35 = 38.45 M
3. Embedded Mode
E = 3.6 (400)1.20 = 4772.81 PM
D = 2.5 (4772.81)0.32 = 37.59 M

## Slide 23: Intermediate COCOMO Model
The basic COCOMO model assumes that the effort is only a function of the number of lines of code and some constants evaluated according to the different software system.
However, in reality, no system’s effort and schedule can be solely calculated on the basis of Lines of Code. For that, various other factors such as reliability, Experience, Capability are known as Cost Drivers which can not be measured using LOC.
The Intermediate Model utilizes 15 such drivers for cost estimation.

## Slide 24: Equations for Intermediate COCOMO Model
E
D
P
The project manager is to rate these 15 different parameters for a particular project on six point rating scale (Very Low (VL), Low (L), Nominal (N), High (H), Very High (VH), Extra High (EH)). Then, based on these ratings, appropriate cost driver values are taken from the above table. These 15 values are then multiplied to calculate the EAF (Effort Adjustment Factor).

## Slide 25: Values of Coefficient a, b, c, and d for Intermediate COCOMO Model
Software project | a | b | c | d
Organic | 3.2 | 1.05 | 2.5 | 0.38
Semi detached | 3.0 | 1.12 | 2.5 | 0.35
Embedded | 2.8 | 1.20 | 2.5 | 0.32

## Slide 26: SELF-ASSESSMENT QUESTIONS
1. Describe project estimation.
2. Differentiate between FP and LOC
3. Summarize the COCOMO Software Estimation Model

## Slide 27: REFERENCES FOR FURTHER LEARNING OF THE SESSION
TEXTBOOKS:
1. Roger S.Pressman, “Software Engineering – A Practitioner’s Approach” 7th Edition, Mc Graw Hill,(2014).
2. Ian Sommerville, “Software Engineering”, Tenth Edition, Pearson Education, (2015).
3. Agile Software Development Ecosystems, Jim Highsmith, Addison Wesley; ISBN: 0201760436; 1st edition
Reference Book
Agile Modelling: Effective Practices for Extreme Programming and the Unified Process Scott Amber John Wiley & Sons; ISBN: 0471202827; 1st edition.
WEB REFERNCES/MOOCS:
https://www.digite.com/kanban/what-is-kanban/
http://www.scaledagileframework.com
https://www.guru99.com/test-driven-development.html
https://junit.org/junit5/

## Slide 28
THANK YOU
Team – ADAPTIVE SOFTWARE ENGINEERING